1. Project Initiation

- 1.1 Define project purpose and scope

- 1.2 Secure project sponsorship

- 1.3 Identify stakeholders

- 1.4 Develop the project charter

- 1.5 Approval of the project charter

- 1.6 Identify and secure core resources (team, tools)

- 1.7 Conduct project kick-off meeting

- 1.8 Completion of the initiation

2. Requirements Analysis

- 2.1 Conduct stakeholder needs analysis

- 2.2 Identify functional and non-functional requirements

- 2.3 Outline data synchronization and security requirements

- 2.4 Specify user account and cart synchronization features

- 2.5 Draft initial budget and timeline

- 2.6 Obtain stakeholder approval on requirements and timeline

3. System Design

- 3.1 Develop UI/UX design specifications (mobile app and website)

  - 3.1.1 Create wireframes and design mockups

  - 3.1.2 Ensure seamless browsing, searching, and cart management

- 3.2 Design functional components (payment, notifications)

- 3.3 Develop data synchronization architecture (across mobile app and website)

- 3.4 Obtain approval on design and architecture

4. Development

- 4.1 Setup development environment

- 4.2 Develop mobile application (iOS & Android) functionalities

  - 4.2.1 Shopping and cart management features

  - 4.2.2 Payment gateway integration

  - 4.2.3 Delivery and shipping options

- 4.3 Develop optimized mobile website functionalities

- 4.4 Synchronize user accounts and cart across all interfaces

- 4.5 Perform unit testing on individual components

5. Testing

- 5.1 Develop a comprehensive test plan and test cases

- 5.2 Conduct alpha testing (internal testing)

- 5.3 Beta testing with selected customers

  - 5.3.1 Gather and analyze customer feedback

  - 5.3.2 Fix bugs and optimize performance

- 5.4 Conduct performance, stress, and regression testing

- 5.5 Validate synchronization across mobile app, mobile website, and desktop website

6. Training

- 6.1 Develop training materials for end-users and helpdesk staff

  - 6.1.1 User tutorials (account creation, browsing, checkout)

  - 6.1.2 Helpdesk troubleshooting guides

- 6.2 Conduct training sessions for support staff

7. Documentation

- 7.1 Develop system help documentation and FAQs

- 7.2 Create user manuals for mobile app and website

- 7.3 Review and revise documentation based on feedback

8. Pilot Deployment

- 8.1 Identify the pilot user group for the mobile app and website

- 8.2 Deploy a pilot version of the app and website

- 8.3 Collect pilot user feedback and evaluate results

- 8.4 Make final updates based on pilot findings

9. Full Deployment

- 9.1 Confirm deployment readiness

- 9.2 Submit and get approval from Android and Apple stores

- 9.3 Deploy mobile app and website to live environments

- 9.4 Ensure cross-platform synchronization

- 9.5 Announce deployment to all stakeholders

10. Project Close-out

- 10.1 Collect and document lessons learned

- 10.2 Archive all project documents

- 10.3 Set up ongoing maintenance and support team

- 10.4 Finalize and close out project with stakeholders

II

Yes. The structure you provided is a full IT project lifecycle/WBS, but many of its activities are specific to an e-commerce/mobile project. For the St. Luke Foundation Digital Workplace Platform (SL-DWP), I would preserve the same 10-phase logic while replacing the irrelevant activities with activities that correspond directly to your actual Laravel web-based MVP, RBAC, document management, security, testing, and academic capstone constraints.

Most importantly, because your current UoPeople assignment is an 8-week capstone proposal, I would distinguish between the full project lifecycle WBS and the 8-week academic MVP scope. The latter should stop at pilot/prototype evaluation rather than claim full organizational deployment.

## Refined SL-DWP Project WBS

### 1. Project Initiation

| ID | Activity | SL-DWP Application | Deliverable |
| --- | --- | --- | --- |
| 1.0 | Project Initiation | Establish the foundation of the SL-DWP project | Initiation package |
| 1.1 | Define project purpose and scope | Define the problem, MVP boundaries, assumptions, and constraints | Preliminary scope |
| 1.2 | Confirm project sponsorship | Identify the organizational/academic sponsor and project authority | Sponsorship confirmation |
| 1.3 | Identify stakeholders | Identify leadership, administrators, managers, employees, IT personnel, researcher, and test participants | Stakeholder register |
| 1.4 | Develop project charter | Document purpose, objectives, scope, stakeholders, constraints, risks, and success criteria | Project charter |
| 1.5 | Review/approve project charter | Validate the project direction and scope | Charter approval/baseline |
| 1.6 | Identify and secure core resources | Confirm developer environment, Laravel/PHP, database, Git, ProjectLibre, testing tools, and data resources | Resource plan |
| 1.7 | Conduct project kick-off | Establish project expectations, communication, schedule, and responsibilities | Kick-off record |
| 1.8 | Complete initiation | Confirm readiness for requirements analysis | M1: Initiation complete |

Important adjustment: Because this is an individual MSIT capstone, “project sponsorship” does not necessarily mean a formal corporate sponsor. It can represent the academic/project authority and organizational stakeholder relationship. Do not claim formal St. Luke approval unless you actually have it.

# 2. Requirements Analysis

This phase is particularly important because your assignment explicitly requires a clear problem statement, stakeholders, scope, and requirements.

| ID | Activity | SL-DWP Application | Deliverable |
| --- | --- | --- | --- |
| 2.0 | Requirements Analysis | Determine what the MVP must provide | Requirements baseline |
| 2.1 | Conduct stakeholder needs analysis | Identify information, communication, document, access-control, and administrative needs | Stakeholder needs analysis |
| 2.2 | Identify functional requirements | Authentication, users, roles, dashboard, directory, announcements, documents, audit logs | Functional requirements |
| 2.3 | Identify non-functional requirements | Security, usability, performance, availability, maintainability | NFR specification |
| 2.4 | Define data and access-control requirements | Identify data entities, relationships, permissions, confidentiality, and retention considerations | Data/security requirements |
| 2.5 | Define RBAC requirements | Establish roles, permissions, resource access, and least-privilege rules | RBAC matrix |
| 2.6 | Define audit and accountability requirements | Identify events requiring logging, such as authentication and administrative actions | Audit requirements |
| 2.7 | Develop preliminary budget and timeline | Estimate resources, incremental costs, milestones, and dependencies | Budget and schedule |
| 2.8 | Validate requirements and schedule | Review requirements against project scope and constraints | Validated baseline |
| 2.9 | Complete requirements analysis | Freeze MVP requirements for design | M2: Requirements baseline |

### Example Functional Requirements

| ID | Requirement |
| --- | --- |
| FR-01 | The system shall authenticate registered users securely. |
| FR-02 | The system shall assign users appropriate roles and permissions. |
| FR-03 | The system shall enforce RBAC at the server/application level. |
| FR-04 | The system shall provide an organizational dashboard. |
| FR-05 | The system shall provide an employee directory. |
| FR-06 | Authorized users shall create and view internal announcements. |
| FR-07 | Authorized users shall upload and access controlled documents. |
| FR-08 | The system shall record selected security and administrative events in audit logs. |

### Example Non-Functional Requirements

| Category | Requirement |
| --- | --- |
| Security | Unauthorized users must not access restricted functions/resources. |
| Usability | Core tasks should be understandable to representative users without extensive training. |
| Performance | Core pages/functions should meet predefined response-time targets under the test conditions. |
| Maintainability | Application components should be modular and documented. |
| Privacy | Development/testing should use synthetic or anonymized data wherever possible. |

# 3. System Design

Your original structure focuses on mobile applications, shopping carts, payment gateways, and synchronization. Those should be completely removed because they are outside the SL-DWP project.

The SL-DWP design phase should instead concentrate on web architecture, RBAC, database design, security, and UI/UX.

| ID | Activity | SL-DWP Application | Deliverable |
| --- | --- | --- | --- |
| 3.0 | System Design | Translate requirements into a technical solution | Design package |
| 3.1 | Develop UI/UX specifications | Design responsive web interface for dashboard and modules | UI/UX specification |
| 3.1.1 | Create wireframes/mockups | Dashboard, login, directory, announcements, documents, administration | Wireframes |
| 3.1.2 | Design navigation and workflows | Ensure consistent navigation and intuitive access to core functions | User flows |
| 3.2 | Design functional components | Authentication, RBAC, users, dashboard, directory, announcements, documents, audit | Component design |
| 3.3 | Design application architecture | Laravel application structure, services, controllers, database, authorization | Architecture |
| 3.4 | Design database | Users, roles, permissions, documents, announcements, audit records | ER/database model |
| 3.5 | Design security architecture | Authentication, authorization, least privilege, validation, session security, logging | Security design |
| 3.6 | Define data access model | Map organizational roles to permitted resources | RBAC/data-access model |
| 3.7 | Design evaluation architecture | Define how functionality, security, usability, and performance will be measured | Evaluation design |
| 3.8 | Review design | Verify design against requirements and scope | Design review |
| 3.9 | Complete system design | Establish implementation baseline | M3: Design baseline |

### Recommended SL-DWP Architecture

┌─────────────────────────┐

│       SL-DWP Users      │

│ Employees / Managers /  │

│ Administrators          │

└────────────┬────────────┘

│

▼

┌─────────────────────────┐

│    Responsive Web UI    │

│ Dashboard / Directory   │

│ Announcements / Docs    │

└────────────┬────────────┘

│

▼

┌─────────────────────────┐

│   Laravel Application   │

│ Authentication          │

│ Authorization / RBAC    │

│ Business Logic          │

│ Validation / Sessions   │

└────────────┬────────────┘

│

┌───────────────┼───────────────┐

▼               ▼               ▼

┌────────────┐  ┌────────────┐  ┌────────────┐

│ Relational │  │ Document   │  │ Audit Log  │

│ Database   │  │ Repository │  │ Records    │

└────────────┘  └────────────┘  └────────────┘

# 4. Development

The development phase should directly correspond to the MVP scope.

| ID | Activity | Deliverable |
| --- | --- | --- |
| 4.0 | MVP Development | Functional application |
| 4.1 | Set up development environment | Laravel/PHP/database/Git environment |
| 4.2 | Implement application foundation | Laravel structure, configuration, routing |
| 4.3 | Implement authentication | Login, logout, sessions, password management |
| 4.4 | Implement user management | User profiles and administrative controls |
| 4.5 | Implement RBAC | Roles, permissions, authorization rules |
| 4.6 | Implement dashboard | Organizational dashboard |
| 4.7 | Implement directory | Staff/user directory |
| 4.8 | Implement announcements | Create, publish, view announcements |
| 4.9 | Implement document repository | Upload, categorize, authorize, retrieve documents |
| 4.10 | Implement audit logging | Record defined security/administrative events |
| 4.11 | Integrate modules | Verify interactions between modules |
| 4.12 | Conduct unit testing | Test individual components |
| 4.13 | Refine MVP | Fix implementation defects |
| 4.14 | Complete MVP | Integrated application ready for evaluation |

### M4: Integrated MVP

This is a critical milestone because it marks the transition from development to evaluation.

# 5. Testing and Evaluation

I recommend calling this Testing and Evaluation, rather than simply Testing, because your UoPeople assignment specifically expects evidence that the proposed solution can be evaluated.

| ID | Activity | SL-DWP Application |
| --- | --- | --- |
| 5.0 | Testing and Evaluation | Determine whether MVP satisfies defined criteria |
| 5.1 | Develop test plan | Define test methods, cases, participants, and acceptance criteria |
| 5.2 | Functional testing | Authentication, RBAC, directory, announcements, documents, audit |
| 5.3 | Security testing | Authorization, privilege escalation, input validation, session/security controls |
| 5.4 | Performance testing | Response time and basic load behavior |
| 5.5 | Usability evaluation | Representative users perform predefined tasks |
| 5.6 | Analyze test results | Compare results with predefined criteria |
| 5.7 | Correct identified defects | Fix significant defects |
| 5.8 | Regression testing | Verify fixes do not break existing functionality |
| 5.9 | Evaluate feasibility | Technical, operational, economic, security, and usability feasibility |
| 5.10 | Complete evaluation | Document evidence and limitations |

### Proposed Evaluation Criteria

| Evaluation Area | Example Measure |
| --- | --- |
| Functional | ≥95% of core test cases pass |
| Authorization | 100% of tested restricted resources deny unauthorized access |
| Security | No unresolved critical security defect identified during planned testing |
| Usability | Representative participants complete predefined core tasks |
| Performance | Core operations meet predefined response-time thresholds |
| Feasibility | Findings documented against technical, operational, economic, and security criteria |

These thresholds should be defined before testing, rather than selected after seeing the results.

### M5: Evaluation Complete

# 6. Training

For your academic MVP, training should be kept small. You should not promise organization-wide training.

| ID | Activity | Deliverable |
| --- | --- | --- |
| 6.0 | Prototype Training/Orientation | Basic user guidance |
| 6.1 | Prepare quick-start materials | Short user guide |
| 6.1.1 | Document login and navigation | Login/navigation guide |
| 6.1.2 | Document core workflows | Directory, announcements, documents |
| 6.2 | Conduct limited prototype orientation | Demonstration/feedback session |
| 6.3 | Document training observations | Training feedback |

Out of scope: organization-wide training of all St. Luke personnel.

This distinction is important for maintaining feasibility.

# 7. Documentation

Documentation should be an explicit WBS component because it is both a capstone deliverable and a requirement for maintainability.

| ID | Activity | Deliverable |
| --- | --- | --- |
| 7.0 | Documentation | Project documentation |
| 7.1 | Document system architecture | Architecture documentation |
| 7.2 | Document database design | ERD/schema documentation |
| 7.3 | Document RBAC | Role/permission matrix |
| 7.4 | Document installation/configuration | Technical setup guide |
| 7.5 | Develop user documentation | User guide |
| 7.6 | Document testing | Test cases/results |
| 7.7 | Document security controls | Security documentation |
| 7.8 | Document limitations | Known limitations |
| 7.9 | Finalize academic documentation | Capstone report |

# 8. Pilot Evaluation

This is where I would make a major change from your example.

Your project should not claim a production pilot deployment across St. Luke during an eight-week capstone.

Instead:

| ID | Activity | SL-DWP Approach |
| --- | --- | --- |
| 8.0 | Prototype Pilot Evaluation | Controlled evaluation |
| 8.1 | Define representative pilot group | Small group of representative users |
| 8.2 | Provide controlled MVP access | Development/test environment |
| 8.3 | Execute predefined user tasks | Directory, announcements, documents, dashboard |
| 8.4 | Collect usability feedback | Structured questionnaire/interview |
| 8.5 | Analyze findings | Identify usability and functional issues |
| 8.6 | Implement feasible refinements | Correct significant issues |
| 8.7 | Document pilot findings | Evaluation report |

### M6: Pilot Evaluation Complete

The term pilot evaluation is preferable to “pilot deployment” because you are evaluating a prototype rather than deploying a production enterprise platform.

# 9. Deployment

For the current MSIT capstone, I would change this from Full Deployment to Deployment Readiness / Future Deployment Planning.

| ID | Activity | SL-DWP Application |
| --- | --- | --- |
| 9.0 | Deployment Readiness | Determine whether future deployment is justified |
| 9.1 | Assess deployment readiness | Technical/security/operational review |
| 9.2 | Document production requirements | Hosting, backup, monitoring, security |
| 9.3 | Identify future infrastructure needs | Hosting, domain, SSL, database, backup |
| 9.4 | Develop deployment recommendations | Production deployment roadmap |
| 9.5 | Identify organizational adoption requirements | Governance, training, support |
| 9.6 | Document future integrations | Potential Microsoft 365/Teams/API integration |
| 9.7 | Finalize deployment recommendation | Go-forward recommendations |

### Why this is better

Your current project does not need:

- Apple App Store approval

- Google Play approval

- mobile application deployment

- production-wide deployment

- organization-wide announcement

- full infrastructure migration

Those activities belong to a future implementation project.

# 10. Project Close-out

| ID | Activity | Deliverable |
| --- | --- | --- |
| 10.0 | Project Close-out | Closure package |
| 10.1 | Analyze project results | Findings |
| 10.2 | Document lessons learned | Lessons-learned register |
| 10.3 | Compare objectives with results | Objective achievement analysis |
| 10.4 | Document limitations | Limitation analysis |
| 10.5 | Archive project artifacts | Code/documentation/test artifacts |
| 10.6 | Identify future improvements | Enhancement roadmap |
| 10.7 | Present final results | Final presentation |
| 10.8 | Complete project closure | M7: Project closed |

# Consolidated SL-DWP WBS

This is the version I recommend using as your master WBS in ProjectLibre.

| WBS | Phase | Main Output | Timing |
| --- | --- | --- | --- |
| 1.0 | Project Initiation | Project charter | W1 |
| 2.0 | Requirements Analysis | Requirements baseline | W1–W2 |
| 3.0 | System Design | Design baseline | W3 |
| 4.0 | MVP Development | Integrated MVP | W4–W6 |
| 5.0 | Testing & Evaluation | Evaluation results | W7 |
| 6.0 | Training/Orientation | User guidance | W7–W8 |
| 7.0 | Documentation | Technical/project documentation | W6–W8 |
| 8.0 | Pilot Evaluation | Pilot findings | W7–W8 |
| 9.0 | Deployment Readiness | Future deployment plan | W8 |
| 10.0 | Project Close-out | Final project package | W8 |

## Major Milestones

| Milestone | Description | Target |
| --- | --- | --- |
| M1 | Initiation complete | End W1 |
| M2 | Requirements baseline | End W2 |
| M3 | Design baseline | End W3 |
| M4 | Integrated MVP | End W6 |
| M5 | Evaluation complete | End W7 |
| M6 | Pilot evaluation complete | W8 |
| M7 | Final delivery/project closure | End W8 |

## Recommended Critical Path

1.0 Initiation

↓

2.0 Requirements

↓

3.0 System Design

↓

4.0 MVP Development

↓

5.0 Testing & Evaluation

↓

8.0 Pilot Evaluation

↓

9.0 Deployment Readiness

↓

10.0 Project Close-out

Some activities such as documentation, training materials, and risk management can run in parallel. They should therefore not unnecessarily extend the critical path.

## What I would change from your original 10-phase model

| Original Activity | SL-DWP Decision | Reason |
| --- | --- | --- |
| Mobile iOS/Android development | Remove | Not part of SL-DWP MVP |
| Shopping/cart management | Remove | E-commerce functionality is out of scope |
| Payment gateway | Remove | Not applicable |
| Delivery/shipping | Remove | Not applicable |
| Mobile/website synchronization | Replace | Use data/access-control architecture for the web platform |
| Customer beta testing | Replace | Representative stakeholder/user evaluation |
| App Store submission | Remove | No mobile app |
| Google Play submission | Remove | No mobile app |
| Full production deployment | Defer | Beyond 8-week capstone scope |
| Organization-wide training | Defer | Beyond MVP scope |
| Helpdesk team | Future phase | Not required for prototype |
| User documentation | Keep | Important capstone deliverable |
| Security testing | Strengthen | Central to SL-DWP |
| RBAC design/testing | Strengthen | Core system requirement |
| Audit logging | Strengthen | Supports accountability/security |
| Feasibility assessment | Strengthen | Explicit UoPeople requirement |
| Pilot evaluation | Keep, but controlled | Provides evidence without claiming production deployment |

### The most important conceptual refinement

Your project is not:

"Build and deploy a complete digital workplace for St. Luke."

It is:

"Design, develop, and evaluate a secure web-based MVP of a role-based digital workplace platform for St. Luke Foundation, demonstrating the technical feasibility of centralized organizational information, communication, controlled document access, and basic administrative coordination within an eight-week capstone project."

That wording makes the scope, feasibility, evaluation criteria, and academic level much clearer.

It also gives you a strong connection between your problem statement → requirements → WBS → Gantt → development → testing → evaluation → conclusion, which is exactly the traceability you want in an MSIT capstone.

Yes — that changes the project definition significantly. If your actual goal is to build and deploy a complete digital workplace for St. Luke Foundation, then we should not artificially reduce the project to an academic prototype.

The better approach is to distinguish between:

- The project vision: Build and deploy a complete SL-DWP for St. Luke.

- The capstone implementation: Establish the architecture, build the core platform, validate it, and progress toward deployment within the available project period.

- Future releases: Features that require additional implementation after the initial release can be managed as subsequent releases rather than being labeled permanently “out of scope.”

### Revised project statement

The St. Luke Foundation Digital Workplace Platform (SL-DWP) project aims to design, develop, deploy, and establish a secure, centralized digital workplace that enables St. Luke Foundation's geographically distributed staff and management to access organizational information, communicate internally, manage documents, coordinate activities, and use role-based digital services through a unified web platform.

This means your WBS should represent a real organizational IT implementation, not merely a student prototype.

## Revised 10-phase project structure

### 1. Project Initiation

1.1 Define project purpose, business case, and scope
1.2 Secure executive/project sponsorship
1.3 Identify stakeholders
1.4 Develop project charter
1.5 Approve project charter
1.6 Establish project governance
1.7 Identify project team and technical resources
1.8 Establish communication and reporting procedures
1.9 Conduct project kick-off
1.10 Complete initiation

Milestone: M1 – Project Charter Approved

### 2. Requirements Analysis

2.1 Conduct organizational needs assessment
2.2 Analyze stakeholder requirements
2.3 Analyze existing workflows and information systems
2.4 Identify functional requirements
2.5 Identify non-functional requirements
2.6 Define security and privacy requirements
2.7 Define organizational roles and permissions
2.8 Develop RBAC/data-access model
2.9 Define document-management requirements
2.10 Define communication requirements
2.11 Define reporting/dashboard requirements
2.12 Define integration/API requirements
2.13 Define data migration requirements
2.14 Develop preliminary budget and schedule
2.15 Validate requirements with stakeholders
2.16 Approve requirements baseline

Milestone: M2 – Requirements Baseline Approved

### 3. System Architecture and Design

3.1 Develop overall system architecture
3.2 Define application architecture
3.3 Design database architecture
3.4 Design RBAC/authorization architecture
3.5 Design security architecture
3.6 Design document-management architecture
3.7 Design notification/communication architecture
3.8 Design API/integration architecture
3.9 Design backup and disaster-recovery architecture
3.10 Design deployment/hosting architecture
3.11 Develop UI/UX specifications
3.11.1 Login/authentication interfaces
3.11.2 Dashboard
3.11.3 Employee directory
3.11.4 Announcements
3.11.5 Document management
3.11.6 Administration
3.11.7 Reporting
3.12 Develop wireframes and prototypes
3.13 Conduct architecture/design review
3.14 Approve system architecture and design

Milestone: M3 – Design Baseline Approved

### 4. Platform Development

4.1 Establish development, testing, and staging environments
4.2 Implement application foundation
4.3 Implement authentication and identity management
4.4 Implement user management
4.5 Implement RBAC and permissions
4.6 Implement organizational structure
4.7 Implement dashboard
4.8 Implement employee directory
4.9 Implement announcements and internal communication
4.10 Implement document repository
4.11 Implement document permissions/versioning
4.12 Implement audit logging
4.13 Implement notifications
4.14 Implement search
4.15 Implement reporting and KPIs
4.16 Implement administrative functions
4.17 Implement backup and recovery mechanisms
4.18 Develop APIs/integration services
4.19 Integrate platform components
4.20 Conduct unit testing

Milestone: M4 – Feature-Complete Release

### 5. Testing and Quality Assurance

5.1 Develop master test plan
5.2 Develop test cases
5.3 Functional testing
5.4 Integration testing
5.5 Database testing
5.6 Security testing
5.7 RBAC/authorization testing
5.8 Vulnerability testing
5.9 Performance/load testing
5.10 Backup/recovery testing
5.11 Usability testing
5.12 Accessibility testing
5.13 User Acceptance Testing (UAT)
5.14 Record defects
5.15 Correct defects
5.16 Regression testing
5.17 Obtain UAT approval

Milestone: M5 – UAT Approved

### 6. Training and Change Management

6.1 Develop implementation/change-management plan
6.2 Identify user groups
6.3 Develop training materials
6.4 Develop administrator training
6.5 Develop manager training
6.6 Develop employee training
6.7 Develop helpdesk/support procedures
6.8 Conduct administrator training
6.9 Conduct manager training
6.10 Conduct employee training
6.11 Collect training feedback
6.12 Update training materials

### 7. Documentation

7.1 Technical architecture documentation
7.2 Database documentation
7.3 Security documentation
7.4 API documentation
7.5 System administration guide
7.6 User manual
7.7 Helpdesk guide
7.8 Backup/recovery procedures
7.9 Disaster-recovery documentation
7.10 Security incident procedures
7.11 Maintenance documentation
7.12 Finalize system documentation

### 8. Pilot Deployment

8.1 Define pilot sites/departments
8.2 Prepare production infrastructure
8.3 Configure production environment
8.4 Deploy pilot release
8.5 Configure users and roles
8.6 Migrate approved pilot data
8.7 Conduct pilot training
8.8 Monitor pilot operation
8.9 Collect user feedback
8.10 Analyze pilot performance
8.11 Resolve pilot issues
8.12 Approve production rollout

Milestone: M6 – Pilot Approved

### 9. Full Deployment

9.1 Confirm production readiness
9.2 Finalize deployment plan
9.3 Finalize data migration
9.4 Configure all organizational roles/users
9.5 Deploy production platform
9.6 Activate organizational modules
9.7 Validate security and access controls
9.8 Validate backups and monitoring
9.9 Conduct post-deployment verification
9.10 Announce platform availability
9.11 Provide post-deployment support
9.12 Monitor adoption and system performance
9.13 Conduct post-implementation review

Milestone: M7 – SL-DWP Production Deployment

### 10. Project Close-out and Operations Transition

10.1 Collect lessons learned
10.2 Evaluate project objectives and KPIs
10.3 Complete final project documentation
10.4 Archive project records
10.5 Transfer system ownership
10.6 Establish ongoing IT support
10.7 Establish maintenance procedures
10.8 Establish security monitoring
10.9 Establish backup/recovery operations
10.10 Establish enhancement/change-request process
10.11 Develop future-release roadmap
10.12 Obtain stakeholder acceptance
10.13 Formally close project

Milestone: M8 – Project Closed / Operations Transitioned

## This also changes your scope

I would no longer put these automatically under "out of scope":

- full deployment

- user training

- data migration

- production infrastructure

- system administration

- maintenance

- notifications

- reporting

- APIs

- integrations

- backup/recovery

- organizational rollout

They are now legitimate components of your complete digital workplace project.

However, you still need scope boundaries. "Complete digital workplace" does not mean "every possible St. Luke information system."

For example:

| Capability | Complete SL-DWP |
| --- | --- |
| Authentication | ✅ |
| User management | ✅ |
| RBAC | ✅ |
| Organizational directory | ✅ |
| Dashboard | ✅ |
| Announcements | ✅ |
| Document management | ✅ |
| Search | ✅ |
| Notifications | ✅ |
| Audit logging | ✅ |
| Reporting/KPIs | ✅ |
| Workflow/coordination | ✅ |
| APIs | ✅ |
| Backup/recovery | ✅ |
| Administration | ✅ |
| Training | ✅ |
| Production deployment | ✅ |
| Pilot rollout | ✅ |
| Organization-wide rollout | ✅ |
| Medical records | ❌ Separate specialized system |
| Payroll | ❌ Separate system |
| Accounting/ERP | ❌ Separate system |
| Full hospital information system | ❌ Separate system |
| Full school information system | ❌ Separate system |
| E-commerce platform | ❌ Separate system |
| Advanced AI platform | ❌ Future extension |

That distinction is important: complete digital workplace ≠ complete enterprise ERP/HMIS/SIS.

### I would therefore rename your project

Instead of:

St. Luke Foundation Digital Workplace Platform MVP

use:

St. Luke Foundation Digital Workplace Platform (SL-DWP)

And your project objective becomes:

To design, develop, deploy, and transition to operational use a secure, centralized, role-based digital workplace platform for St. Luke Foundation that integrates organizational information, internal communication, document management, user access control, reporting, and selected coordination services across its geographically distributed operations.

This is a much stronger real-world IT project and also gives your MSIT capstone a credible progression from requirements → architecture → development → testing → training → pilot → production deployment → operations.

For your UoPeople assignment, I would still present the 8-week schedule as the initial implementation/research phase, while the master WBS above represents the complete SL-DWP project lifecycle. That resolves the apparent conflict between your ambition to actually deploy the system and the assignment's limited planning period.